## General Equipment
General Equipment
*This checklist is supplemental material to the Core Biorisk Management Documents provided by Sandia National Laboratories. It provides a general task list for the installation of new equipment. This task list does not have to be completed in the order shown here. For more detailed information and guided stepwise approach, please refer to the Core Biorisk Management Document Templates (https://gcbs.sandia.gov/core-documents/).
Task | Responsibility for Task Completion | Due Date | Completion Date | Comments
Risk Assessment
Conduct protocol risk assessment for work to be done
Determine appropriate equipment based on risk assessment
Determine if there's adequate funding to purchase, certify, operate, and maintain the instrument
Determine location and space requirements
[Instrument Name Here]
Facility / Information Technology (IT) Requirements
Coordinate with facilities management for delivery and installation
Obtain power requirements (including voltage and plug compatability between new equipment and facility)
Obtain instrument operating requirements (temperature, humidity)
Determine any additional utilities required for operation (vacuum, water, drain, vents, others)
Determine power supply back-up requirements (uninterruptible power supply (UPS), generator connected outlets, others)
Determine IT requirements from vendor (network connection, file storage, LIS integration, others)
Notify facilities group of intention to obtain new equipment and discuss requirements
Notify IT group of intention to obtain new equipment and discuss requirements
Acquire IT specifications from vendor
User Requirements
Identify and order calibration and/or verification material
Identify and order necessary reagents
Identify and order necessary personal protective equipment (PPE)
Document vendor service agreements or maintenance contract
Identify any additonal mechanical, electrical, plumbing (MEP) requirements (air, gas, ethernet, high efficiency particulate air (HEPA) filters, ducts, others)
Ensure access controls and signage are appropriate to protect staff and equipment
Equipment Reciept
Add new equipment to relevant inventory lists
Uniquely label, mark, or otherwise identify equipment
Keep all documentation, note date received, copy and return warranty to manufacturer
Schedule installation qualification, if applicable
Post vendor contact information on the equipment
Documentation
Draft and test Standard Operating Procedure(s)
Draft a training plan
Create training logs
Create a competency assessment form to ensure training
Create maintenance and calibration logs
Create vendor service logs
Identify and print/catalog Safety Data Sheets (SDS)
Identify and/or create necessary job aids
Identify vendor specific manuals (operations, maintenance, others) for equipment, reagents, and consumables
Create incident report logs
Establish procedures for responding to manufacturer's recalls/notices and manufacturer recommended actions
Identify and review equipment records
Create inventory management system/log for reagents/consumables
Designate reviewers for above mentioned documentation & location for storage
Calibration Testing
Schedule annual calibration/certification testing
Identify personnel and/or company responsible for calibration testing
Determine what tests are necessary to complete for calibration testing
Maintenance
Develop maintenance schedule
Assign maintenance
Prepare routine cleaning and/or decontamination instructions
Obtain a supply of commonly needed spare parts
Training
Identify key operators/trainers/appropriate staff members
Schedule training
Prepare training materials
Train key operators
Assess competency of key operators
Train staff members
Assess competency of staff members
Confirm completion of all training and competency
External Instrument Support
Identify and record vendor contact info for easy retrieval
Identify instrument(s) to be used when initial instrument is out of commission
If no available back up instrument(s), identify appropriate off-site facility where work can continue

## Equipment Records Checklist
Equipment Records
Record Type | Responsibility for Information Recording | Due Date | Completion Date | Comments
Based on ISO 15189:2022
General Equipment Records
Manufacturer/supplier details and sufficient information to uniquely identify each item of equipment, including software
Dates of receipt, acceptance testing, and entering into service
Evidence that equipment conforms with specified acceptability criteria
Current location
Condition when received
Manufacturer's instructions
Preventive maintenance program
Maintenance activities performed by the laboratory or approved external service provider
Equipment damage, malfunction, modification, or repair
Equipment Performance/Status Records
General performance reports
Calibration certificates (including dates, times, and results)
Verification certificates (including dates, times, and results)
Equipment status (such as active or in-service, out-of-service, quarantined, retired, obsolete)

## Resources
Resource | URL
Referenced in this Document
WHO Laboratory Biosafety Manual Fourth Edition | https://www.who.int/publications/i/item/9789240011311
ISO 15189:2022 | https://www.iso.org/standard/76677.html
NSF/ANSI 49-2022 | https://webstore.ansi.org/standards/nsf/nsfansi492022?source=blog&_gl=1*wdzgls*_gcl_au*MTM2OTg0MTMwMS4xNzI3MjgyMTQ5
Core Documents
Sandia National Laboratories: Core Biorisk Management Document Templates | https://gcbs.sandia.gov/core-documents/